Working group to define a framework for practice for the provision of family integrated care in the neonatal unit

# Terms of Reference

# Background, general terms and purpose

# This Framework for Practice aims to provide guidance on the implementation of a family centred approach to care in the neonatal unit (so called family integrated care). The working group will review existing evidence and examples of good practice drawn from a variety of neonatal settings (NICU / LNU / SCU) both nationally and internationally. This work will inform the development of a series of recommendations that individual units and networks can use as a basis for the implementation and ongoing provision of family integrated care (FIC).

# Outputs

# The working group will specifically

# Review the existing literature / evidence base around the provision of FIC

# Review existing examples of good practice and differing models of delivering FIC

# Review parental experiences and perceptions of FIC

# Use the above to inform the development of a Framework for Practice for the  implementation of FIC

# Develop and / or highlight existing useful educational resources

# Membership

# The composition of the group will be as follows:

# Chair: Dr Judith Simpson, Glasgow. BAPM EC rep for Scotland

# Members:

# Dr Liz McKechnie, Consultant Neonatologist, Leeds (Representing International FIC Steering Group) (Invited)

# Consultant representation from Imperial College, London (Invited)

# Dr Neil Patel, Consultant neonatologist, Glasgow (Invited)

# 1-2 other medical representatives (Consultants and Trainees - we are particularly interested in applications from LNU / SCBU staff.)

# 2 nursing / ANNP representatives

# 1- 2 parent representatives

# Kate Dinwiddy, Chief Executive of BAPM

# Meetings and Timeline

# It is envisaged that there will be two face-to-face meetings at the RCPCH in London, with development and finalisation of the Framework by teleconference or email correspondence. The following timeline is proposed:

# January 2020 face to face meeting and first draft of framework

# Jan- March 2020 – circulation of repeated versions of the Framework every 2-3 weeks to refine the document by consensus

# March / April– tabled at EC finalisation for consultation

# April / June 2020 – circulated for consultation any proposed changes circulated in real time

# June 2020 – Final document agreed

# June – July 2020 Member consultation

# September 2020 Final Document published.

# BAPM will reimburse reasonable expenses for attending face-to-face meetings, as per BAPM expenses policy. It is expected that individuals will exercise discretion in booking tickets in advance, and seek to travel by the most economical practical route.

# Success Criteria and Measures

# To produce an agreed document

# Reporting

# Circulation to EC and membership as above

# Responsibility and Accountability

# The group is responsible to the BAPM Executive Committee and accountable to the BAPM membership.

# Probity

# The group will operate under the arrangements for probity as set out in the BAPM conflicts of interest policy. All group members will be required to complete a declaration of interest form which will be held in the BAPM office and made available on request.